## EHDS Implementation Roadmap
EHDS Implementation Roadmap - Belgium (CareSets & BIHR Mapping)
Belgian Context |  |  |  | EHDS Mapping |  |  | Implementation Planning |  |  |  | Status
Implementation Year BE |  | BIHR section | CareSet Belgium | EHDS Dataset | EHDS section | EHDS Wave | Approbation CG | Implementation Authentic Source | Authentic Source | Implementation Softs
2025 | ● | Vaccinations | BeVaccination | Patient Summary | Immunisations | Wave 1 (2029) | 2024-04-12 | 2025-07-15 | Regional Vaults | 2025-10-15 | Roll-Out in production
| ● | Laboratory results | BeObservationLaboratory | Medical results | Medical results | EHDS Wave | n/a | n/a | Laboratory + Hubs | 2025-12-31 | Roll-Out in production
2026 | ● | Medication | BeMedication | Patient Summary | Medication summary | Wave 1 (2029) | 2025-10-14 | 2026-07-15 | Regional Vaults | 2026-10-15 | Development Ongoing
| ● | Medication | BEMedicationRequest | ePrescription | ePrescription | Wave 1 (2029) | 2025-10-14 | 2026-07-15 | Recip-e | 2026-10-15 | Development Ongoing
| ● | Medication | BEMedicationDispense | eDispensation | eDispensation | Wave 1 (2029) | 2025-10-14 | 2026-07-15 | Recip-e | 2026-10-15 | Development Ongoing
| ● | Allergy | BeAllergy | Patient Summary | Allergies and intolerances | Wave 1 (2029) | 2024-04-12 | 2025-01-15 | Regional Vaults | 2025-04-15 | Development Ongoing
| ● | DRP Nurse | BeReferral | n/a | n/a | n/a | 2025-10-14 | 2026-02-15 | eReferral (NIHDI) | 2026-04-15 | Development Ongoing
| ● | PSS Antimicrobio | BePSS | n/a | n/a | n/a | 2026-02-10 | 2026-03-15 | PSS (NIHDI) | 2026-08-15 | Development Ongoing
| ● | Patient Will | BePatientWill | Patient Summary | Advance Directives | Wave 1 (2029) | 2025-02-11 | 2025-11-15 | Regional Vaults | 2026-02-15 | Development To Be Started
2027 | ● | Procedure | BeProcedure | Patient Summary | Procedures | Wave 1 (2029) | 2026-02-10 | 2026-11-15 | Regional Vaults | 2027-02-15 | Development To Be Started
| ● | (Tele)monitoring data | BeObservation | n/a | n/a | n/a | 2026-02-10 | 2026-11-15 | Hubs | 2027-02-15 | Development To Be Started
| ● | Problem List | BeProblem | Patient Summary | Medical problems | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
| ● | Implants | BeMedicalDevice | Patient Summary | Medical devices and implants | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
2028 | ● | TBD | BeObservation | Patient Summary | Functional status | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
| ● | TBD | BeObservation | Patient Summary | Pregnancy history | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
| ● | Social factors/Family context | BeObsSocial | Patient Summary | Social history | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
| ● | Care plan & care team | BeCarePlan | Patient Summary | Care plans | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
| ● | TBD | BeObservation | Patient Summary | Observation results | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis in Progress
| ● | TBD | BePatientStory | Patient Summary | Patient story | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis to be Started
| ● | TBD | BeAlert | Patient Summary | Alerts | Wave 1 (2029) |  |  | Regional Vaults |  | Analysis to be Started
| ● | TBD | BeObservation | Patient Summary | Travel history | Wave 1 (2029) | 2026-02-10 | 2026-11-15 | Regional Vaults | 2027-02-15 | Development To Be Started
| ● | Clinical data | BeClinicalObservation | n/a | n/a | n/a | 2026-02-10 | 2026-11-15 | Regional Vaults | 2027-02-15 | Development To Be Started
| ● | Life goals | BeLifeGoal | n/a | n/a | n/a |  |  | Regional Vaults |  | Analysis to be Started
| ● | BelRAI assessment | BeEvaluationScale | n/a | n/a | n/a |  |  | BelRAI (SPF) |  | Analysis in Progress
| ● | Discharge Reports | Discharge Reports | Discharge report | Discharge report | Wave 2 (2031) |  |  | Hubs |  | Analysis in Progress
| ● | Medical imaging | Medical imaging | Imaging | Imaging | Wave 2 (2031) |  |  | Hubs |  | Analysis in Progress